## 2025
Sr | Client Name | Approved Product | Qt.ID | Inv.ID | Payment Date | Quotation Value | Unit ID | Assigned PM | Sales Engineer | Account Manager | Assigned Contractor | Contractual Duration | Progress % | Construction Cost | Target Margin % | Profit Margin% | Buffer/Defecit Value | Case Notes
1 | Hoda Abdelaziz Ahmed Mahgoub | SOG | 18027 | 9621 | 2025-01-01 | 390949.85 | ASV-162A | Ahmed Sallam | Engy Sameh | Menna Middany | External | 40 | 30% | 274948.62 | 20% | 29.67% | 37811.26
2 | Rana-Dania-Deema Mahmoud Abdelbasset- | SOG | 18029 | 9622 | 2025-01-01 | 232640.63 | GV-54 | Rafik |  | Mazen Kamal | Redsea Marine | 30 | 30% | 171482.85 | 20% | 26.29% | 14629.654
3 | Hesham Elbeltagy | Design Fees | 18026 | 9623 | 2025-01-01 | 17100 | K1-1C-0-2 | #N/A | Engy Sameh | Yehia | Design Fees | 0 | 30% | 0 | 20% | 100% | 13680
4 | Nader Rafaat Wagdi Ragheb | SOG | 18034 | 9624 | 2025-01-01 | 659510.58 | GV-24 | Rafik | Engy Sameh | Farah | Redsea Marine | 70 | 30% | 504228.9 | 20% | 23.54% | 23379.564
5 | Wael Riad Nasr | Fixed Jetty | 18028 | 9625 | 2025-01-01 | 10734.15 | ASV-145 | Ahmed Sallam | Haidy Ali | Ulfat | External | 90 | 30% | 124999.88 | 50% | 76.51% | 141099.7
6 | Sherine Morsi | SOG | 18037 | 9626 | 2025-01-01 | 541563.75 | S-21 | Rafik | Nadine Ghoneim | Youssef El sheaty | Redsea golf | 60 | 30% | 426431.25 | 20% | 21.26% | 6819.75
7 | Sherif Mohamed Abdel El Kader | Pool | 16732 | 9627 | 2025-01-01 | 204750 | FD-221 | Mohamed Assal | Maryam Samy | Malak | Profit | 45 | 30% | 0 | 20% | 100% | 163800
8 |  | Design Fees | 17999 | 9628 | 2025-01-01 | 10260 | GV-23B | #N/A |  | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 8208
9 | Hussein Kabany | Design Fees | 17987 | 9629 | 2025-01-01 | 57000 | ASV-126 | #N/A | Haidy Ali | Menna Middany | Design Fees | 0 | 30% | 0 | 20% | 100% | 45600
10 | Ahmed Mohamed Mahmoud El Morsy | Landscape | 17945 | 9630 | 2025-01-01 | 3239793.38 | AH-47B | Youssef | Maryam Samy | Mazen Kamal | Redsea golf | 90 | 30% | 1894441.5 | 20% | 41.53% | 697393.204
11 | Ahmed Mohamed Mahmoud El Morsy | Heater | 17985 | 9631 | 2025-01-01 | 742875 | AH-47B | Youssef | Maryam Samy | Yehia | External | 30 | 30% | 564075 | 20% | 24.07% | 30225
12 | Ahmed Mohamed Mahmoud El Morsy | Softscape | 17986 | 9632 | 2025-01-01 | 254963.1 | AH-47B | Youssef | Maryam Samy | Farah | Softscape | 30 | 30% | 161103.61 | 20% | 36.81% | 42866.87
13 | Ahmed Mohamed Mahmoud El Morsy | Shutter | 17984 | 9633 | 2025-01-01 | 292162.5 | AH-47B | Youssef | Maryam Samy | Ulfat | External | 30 | 30% | 236512.5 | 20% | 19.05% | -2782.5
14 | Mohamed Ahmed El Sayed Abdelhafez Mohamed El Hossary | Landscape | 18043 | 9634 | 2025-01-01 | 257449.5 | K2-6C-0-3 | Ahmed Nasser | Maryam Samy | Youssef El sheaty | Redsea golf | 90 | 30% | 182310.45 | 20% | 29.19% | 23649.15
15 | Khaled Abdelrahem Ahmed | Landscape | 18044 | 9635 | 2025-01-01 | 35437.5 | CY-240B | Mostafa | Engy Sameh | Malak | Profit | 30 | 30% | 0 | 20% | 100% | 28350
16 | Evelin Adly Said-Saad Sobhy Saad Gawargy | Design Fees | 18038 | 9636 | 2025-01-01 | 11400 | S-80C | #N/A | Haidy Ali | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 9120
17 | Hatem Ahmed Ehsan Kotby / Sally Nabile Mohamed Shehata | Shutter | 17884 | 9637 | 2025-01-01 | 210631.2 | GV-65B | Rafik | Maryam Samy | Menna Middany | External | 30 | 30% | 131260.5 | 20% | 37.68% | 37244.46
18 | Maged Micheal Emil / Marian Magdy Shohdy | SOG | 18031 | 9638 | 2025-01-01 | 499722.89 | S-87 | Rafik | Engy Sameh | Mazen Kamal | Redsea golf | 40 | 30% | 408313.5 | 20% | 18.29% | -8535.188
19 | John Moufid Saad / Peter Moufid Saad | Interiors | 18054 | 9639 | 2025-01-01 | 69133.05 | CY-42 | Rafik | Maryam Samy | Yehia | Redsea golf | 35 | 30% | 55965 | 20% | 19.05% | -658.56
20 | Ayman Mamdoh Abass | Design Fees | 18063 | 9640 | 2025-01-01 | 22800 | G-43 | #N/A | Haidy Ali | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 18240
21 | Denis Louis Pierrer Liquiere | Interiors | 18051 | 9641 | 2025-01-01 | 448844.1 | Ph2-Villa-19 | Rafik | Maryam Samy | Ulfat | Redsea golf | 100 | 30% | 343224 | 20% | 23.53% | 15851.28
22 | Nilly Wagdi Karrar | Pool | 18068 | 9642 | 2025-01-01 | 3504375 | FD-47 | Youssef | Nader ElGendy | Youssef El sheaty | Redsea golf | 150 | 30% | 2280296.55 | 20% | 34.93% | 523203.45
23 | Tahra Hassan Fahmi | Outdoor Room | 18061 | 9643 | 2025-01-01 | 1892390.49 | FD-19 | Ahmed Sallam | Nader ElGendy | Malak | Redsea golf | 80 | 30% | 348096 | 40% | 81.61% | 787338.294
24 | Tahra Hassan Fahmi | Unit Extension | 18052 | 9644 | 2025-01-01 | 808782.31 | FD-19 | Ahmed Sallam | Nader ElGendy | Hesham Emshaty | Redsea golf | 80 | 30% | 133770 | 55% | 83.46% | 230182.0395
25 | Omar Salah Eldin Hassan Bassiouny / Amina Omar Salah Eldin Hassan Bassiouny / Aliaa Omar Salah Eldin Hassan Bassiouny | Landscape | 18062 | 9645 | 2025-01-01 | 2068367.44 | FM19A-0-2 | Peter | Engy Sameh | Menna Middany | Redsea Marine | 90 | 30% | 1401821.66 | 20% | 32.23% | 252872.292
26 |  | Design Fees | 18070 | 9646 | 2025-01-01 | 60375 | T1-6 | #N/A |  | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 48300
27 | Osama Mohamed Bahaa El Din | Shutter | 17848 | 9647 | 2025-01-01 | 184167.49 | AH-29B-0 | Omar Nada | Nader ElGendy | Yehia | External | 30 | 30% | 141413.03 | 20% | 23.21% | 5920.962
28 | Danishmand Ahmad | Design Fees | 18003 | 9648 | 2025-01-01 | 42750 | Ph4-Villa-3 | #N/A | Eng. Peter Philip | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 34200
29 | Sherihan Gaballah | Heater | 18071 | 9649 | 2025-01-01 | 495833.1 | CY-110 | Mostafa | Haidy Ali | Ulfat | External | 30 | 30% | 403575 | 20% | 18.61% | -6908.52
30 | Wael Mohamed Mohamed Sayed Khalil | Design Fees | 18074 | 9650 | 2025-01-01 | 25725 | Y-74 | #N/A | Eng. Peter Philip | Youssef El sheaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 20580
31 | KARIM ABOU BAKR WAHBA ELHELALY | SOG | 18079 | 9651 | 2025-01-01 | 95960.16 | CY-215 | Mostafa | Maryam Samy | Malak | Redsea golf | 30 | 30% | 66415.13 | 20% | 30.79% | 10352.998
32 | Ahmed Mohamed Atris Mohamed Abo Dala | Shutter | 18055 | 9652 | 2025-01-06 | 528849.69 | GV-63 | Rafik | Engy Sameh | Hesham Emshaty | External | 60 | 30% | 338446.5 | 20% | 36% | 84633.252
33 | Ahmed Mohamed Atris Mohamed Abo Dala | Landscape | 18056 | 9653 | 2025-01-06 | 420796.69 | GV-63 | Rafik | Engy Sameh | Menna Middany | Redsea Marine | 70 | 30% | 283246.95 | 20% | 32.69% | 53390.402
34 | Ahmed Mohamed Atris Mohamed Abo Dala | Landscape | 18081 | 9654 | 2025-01-06 | 5124313.65 | GV-63 | Rafik | Engy Sameh | Mazen Kamal | Redsea Marine | 80 | 30% | 3934325.85 | 20% | 23.22% | 165125.07
35 | Hussein Hussein mohamed el rashedy | Pool | 18084 | 9655 | 2025-01-06 | 5558437.5 | MB19-A-101 | Rafik | Eng. Peter Philip | Yehia | Redsea Marine | 60 | 30% | 4282853.14 | 20% | 22.95% | 163896.86
36 | Kamel Tarek Amin Malash / Salma Tarek Amin Malash | Infrastructure | 18077 | 9656 | 2025-01-06 | 338743.79 | CY-56 | Mostafa | Engy Sameh | Farah | Maintenance | 90 | 30% | 262302.6 | 20% | 22.57% | 8692.432
37 | Tarek Riad | SOG | 18085 | 9657 | 2025-01-06 | 605735.16 | ASV-183 | Ahmed Sallam | Engy Sameh | Ulfat | Redsea golf | 45 | 30% | 437657.33 | 20% | 27.75% | 46930.798
38 | Wael mohamed Elshahed | Pool | 18086 | 9658 | 2025-01-06 | 198513.53 | AH-36 | Youssef | Engy Sameh | Youssef El sheaty | Redsea golf | 45 | 30% | 101850 | 20% | 0% | 0
39 | Wael mohamed Elshahed | Landscape | 18083 | 9659 | 2025-01-06 | 6497319.26 | AH-36 | Youssef | Engy Sameh | Malak | Maintenance | 30 | 30% | 4085928.91 | 20% | 37.11% | 1111926.498
40 | Mohamed Abdelfattah El Metwally Abdelfattah diab | SOG | 18096 | 9660 | 2025-01-07 | 67593.75 | K2-3T-3 | Ahmed Nasser | Maryam Samy | Hesham Emshaty | Redsea golf | 30 | 30% | 47362.35 | 20% | 29.93% | 6712.65
41 | Abanoub Eid Youseef Ghatas | Design Fees | 18059 | 9661 | 2025-01-08 | 11400 | K2-2C-0-4 | #N/A | Engy Sameh | Menna Middany | Design Fees | 0 | 30% | 0 | 20% | 100% | 9120
42 | Amira El - Sayed | Interiors | 18078 | 9662 | 2025-01-09 | 290443.59 | B-02 | Mostafa | Engy Sameh | Mazen Kamal | Maintenance | 45 | 30% | 231694.53 | 20% | 20.23% | 660.342
43 | Basant -Alaa -Tarek mohamed ahmed hassanein | SOG | 18098 | 9663 | 2025-01-09 | 173906.25 | S-15C | Rafik | Maryam Samy | Yehia | Redsea golf | 40 | 30% | 121149 | 20% | 30.34% | 17976
44 | Ashraf Adel Fouad Ramzy | Design Fees | 17319 | 9664 | 2025-01-09 | 11400 | CY-211A | #N/A | Nader ElGendy | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 9120
45 | Ahmed Hamdy Abou Hashima | Outdoor Room | 18032 | 9665 | 2025-01-09 | 3045520.13 | Ph3-Villa-21 | Mohamed Assal | Engy Sameh | Ulfat | Redsea golf | 120 | 30% | 2946074.78 | 40% | 3.265% | -1118762.702
46 | Ahmed Hamdy Abou Hashima | Landscape | 18033 | 9666 | 2025-01-09 | 633406.67 | Ph3-Villa-21 | Mohamed Assal | Engy Sameh | Youssef El sheaty | Redsea golf | 50 | 30% | 0 | 20% | 100% | 506725.336
47 | Mariam Mohamed Kassem Ahmed El Samny | Design Fees | 18105 | 9667 | 2025-01-12 | 11000 | S78-0-1 | #N/A | Eng. Peter Philip | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 8800
49 | Sara Zobier | Shutter | 18102 | 9669 | 2025-01-13 | 306016.8 | K1-3T-1 | Ahmed Nasser | Engy Sameh | Hesham Emshaty | External | 30 | 30% | 186322.5 | 20% | 39.11% | 58490.94
50 | Karim ElTorkey | Design Fees | 18116 | 9670 | 2025-01-14 | 11000 | K2-4C-0-5 | #N/A | Eng. Peter Philip | Menna Middany | Design Fees | 0 | 30% | 0 | 20% | 100% | 8800
51 | Rana Abdel Hamid Ibrahim Kazamel | SOG | 18129 | 9671 | 2025-01-14 | 6562.29 | CY-254 | Mostafa | Maryam Samy | Mazen Kamal | Profit | 30 | 30% | 15592.5 | 20% | -137.6% | -10342.668
52 | Nevine Zaki | Outdoor Room | 18113 | 9672 | 2025-01-14 | 2235493.16 | AH-51B | Youssef | Haidy Ali | Yehia | Redsea golf | 120 | 30% | 761512.5 | 40% | 65.94% | 579783.396
53 |  | Design Fees | 18135 | 9673 | 2025-01-15 | 11593.8 | Ph2-Villa-39 | #N/A | Eng. Peter Philip | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 9275.04
54 | Bassem darwish | Design Fees | 18095 | 9674 | 2025-01-15 | 27500 | K1-2T-2 | #N/A | Eng. Peter Philip | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 22000
55 | peter Salah | Interiors | 18138 | 9675 | 2025-01-16 | 18624.45 | K1-4T-5 | Ahmed Nasser | Maryam Samy | Youssef El sheaty | Redsea golf | 30 | 30% | 15714.7 | 20% | 15.62% | -815.14
56 | Khaled SOLIMAN | Landscape | 18143 | 9676 | 2025-01-16 | 156298.92 | AH-4 | Omar Nada | Engy Sameh | Malak | Redsea golf | 40 | 30% | 109467.75 | 20% | 29.96% | 15571.386
57 | Mohamed abdallah | Outdoor Room | 18088 | 9677 | 2025-01-16 | 4550429.87 | ASV-177 | Nesma | Haidy Ali | Hesham Emshaty | External | 120 | 30% | 698744.52 | 40% | 84.64% | 2031513.402
58 | Abdalla Khaled | Outdoor Room | 18089 | 9678 | 2025-01-16 | 3841751.64 | ASV-155 | Nesma | Haidy Ali | Menna Middany | External | 120 | 30% | 842537.84 | 40% | 78.07% | 1462513.144
59 | Amin Nabil Amin Messiha El Dahaby | Design Fees | 18131 | 9679 | 2025-01-17 | 11000 | FD-144 | #N/A | Eng. Peter Philip | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 8800
60 | Sanaa Mohamed Shafei Othman | SOG | 18141 | 9680 | 2025-01-17 | 630.77 | JVP-2A | Ahmed Sallam | Nader ElGendy | Yehia | Redsea golf | 30 | 30% | 19682.25 | 20% | 38.63% | 5976.766
61 | Jylan Khairat | SOG | 18124 | 9681 | 2025-01-19 | 462.59 | K2-2C-0-2 | Ahmed Nasser | Haidy Ali | Farah | Redsea golf | 42 | 30% | 17921.04 | 20% | 23.81% | 896.6
62 | Fouad Hassib | Landscape | 18130 | 9682 | 2025-01-20 | 34378.42 | K2-7T-4 | Ahmed Nasser | Engy Sameh | Ulfat | Redsea golf | 70 | 30% | 1182954.15 | 20% | 32.33% | 215521.474
63 | Ahmed Thabet | Floating Jetty | 18082 | 9683 | 2025-01-20 | 22442 | UJ-15 | Peter | Maryam Samy | Youssef El sheaty | External | 90 | 30% | 492343.2 | 50% | 56.86% | 78228.94
64 |  | Design Fees | 18039 | 9684 | 2025-01-21 | 11400 | S-30C | #N/A | Eng. Peter Philip | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 9120
66 | Mary Magdy Gergis | SOG | 18133 | 9686 | 2025-01-22 | 3922.1 | AH-27A-0 | Omar Nada | Engy Sameh | Hesham Emshaty | Redsea golf | 60 | 30% | 144474.75 | 20% | 27.56% | 15071.882
67 | Magdy Mahmoud Shabaan El Adawy | Landscape | 18171 | 9687 | 2025-01-22 | 2169.31 | GV-57 | Rafik | Engy Sameh | Menna Middany | Redsea Marine | 30 | 30% | 67594.8 | 20% | 38.72% | 20650.304
69 | Aliaa Omar | Pool | 18076 | 9689 | 2025-01-22 | 144067.35 | ASV-186 | Nesma | Eng. Peter Philip | Mazen Kamal | Redsea golf | 210 | 30% | 3031494.9 | 20% | 58.62% | 2829003.54
70 | Aliaa Omar | Landscape | 18121 | 9690 | 2025-01-22 | 145129.83 | ASV-186 | Nesma | Eng. Peter Philip | Yehia | Redsea golf | 210 | 30% | 5582300.33 | 20% | 24.36% | 321418.606
71 | Hany Al Moghazy | Infrastructure | 18185 | 9691 | 2025-01-23 | 692.79 | CY-94 | Mostafa | Nadine Ghoneim | Farah | Profit | 30 | 30% | 0 | 20% | 100% | 28181.92
72 | Amin Adly Amin Abdel Meseeh | Pool | 18126 | 9692 | 2025-01-23 | 73690.05 | NS-07B | Rafik | Maryam Samy | Ulfat | Redsea Marine | 200 | 30% | 2170002.18 | 20% | 42.09% | 827626.524
73 | Maha Adly Shukri Tiab | SOG | 18139 | 9693 | 2025-01-23 | 55239.85 | S62-0-4 | Rafik | Maryam Samy | Youssef El sheaty | Redsea Marine | 30 | 30% | 30780.75 | 20% | 44.28% | 13411.13
74 |  | Design Fees | 18148 | 9694 | 2025-01-23 | 220 | Ph4-Villa-66 | #N/A | Eng. Peter Philip | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 8949.352
75 | Amr abuelkher | SOG | 18134 | 9695 | 2025-01-24 | 9024.19 | AH-3B | Engy | Maryam Samy | Hesham Emshaty | Maintenance | 40 | 30% | 386321.52 | 20% | 15.81% | -19227.576
76 | Amr Abdelmeguid | SOG | 18189 | 9696 | 2025-01-24 | 259.8 | K3-5C-0-1 | Ahmed Nasser | Maryam Samy | Menna Middany | Redsea golf | 30 | 30% | 10038 | 20% | 24.01% | 530.376
78 | Mona Mahmoud Abdo Khair El Din | Fixed Jetty | 18153 | 9699 | 2025-01-26 | 7901.25 | W-80 | Peter | Nader ElGendy | Mazen Kamal | External | 90 | 30% | 280970 | 50% | 30.07% | -80086.25
79 | Hisham Oseily | Heater | 18144 | 9700 | 2025-01-26 | 9807 | GV-71A | Rafik | Maryam Samy | Yehia | External | 30 | 30% | 478987.5 | 20% | 3.947% | -80049.724
80 | Mohamed sameh Foad | Landscape | 18192 | 9701 | 2025-01-26 | 4606.55 | AH-14B | Omar Nada | Haidy Ali | Farah | External | 30 | 30% | 83737.5 | 20% | 64.25% | 103651.796
81 | hussein badawy | Design Fees | 18196 | 9702 | 2025-01-28 | 5408.7 | GV-67 | #N/A | Maryam Samy | Ulfat | Design Fees | 0 | 30% | 220000 | 20% | 20.01% | 19.856
82 | Dina Sayed Ahmed Mohamed El Batal / Ali Ahmed Ali Abdelmenaam El Mofty / Jud Ahmed Ali Abdelmenaam El Mofty / Ahmed Ali Abdelmenaam El Mofty | Unit Extension | 18177 | 9703 | 2025-01-28 | 54120.32 | S-06 | Rafik | Engy Sameh | Youssef El sheaty | Redsea golf | 120 | 30% | 1270237.5 | 55% | 53.84% | -31863.375
83 | Amr Essam Hassan Allam | Unit Extension | 18181 | 9704 | 2025-01-28 | 19506.67 | ASV-125 | Ahmed Sallam | Engy Sameh | Malak | Redsea golf | 90 | 30% | 297904.07 | 55% | 69.97% | 148445.017
84 | Amr Essam Hassan Allam | Landscape | 18174 | 9705 | 2025-01-28 | 10348.45 | ASV-125 | Ahmed Sallam | Engy Sameh | Hesham Emshaty | Redsea golf | 60 | 30% | 403126.5 | 20% | 23.39% | 17836.852
85 | Hany Youssef Mohamed El Miseiry | Unit Extension | 18119 | 9706 | 2025-01-29 | 25825.71 | W-43 | Mostafa | Nader ElGendy | Menna Middany | Redsea golf | 120 | 30% | 560544.6 | 55% | 57.31% | 30395.94
86 | Nohal Salah El Din Abdel Halim | Roof Room | 18100 | 9707 | 2025-01-29 | 101441.67 | CY-212B | Engy | Haidy Ali | Mazen Kamal | Redsea golf | 150 | 30% | 1452361.05 | 60% | 71.84% | 610905.71
87 | medhat nassar | Softscape | 18193 | 9708 | 2025-01-30 | 2576.16 | ASV-89A | Ahmed Sallam | Engy Sameh | Yehia | Softscape | 30 | 30% | 99159.89 | 20% | 24.3% | 5635.414
88 | Hnaa Marwan Mohamed Ahmed El Smak / Marwan Mahmoud Ahmed Mohamed Ibrahim El Smak | Interiors | 18186 | 9709 | 2025-01-30 | 610.85 | FM18A-0-1 | Peter | Engy Sameh | Farah | Maintenance | 30 | 30% | 24986.3 | 20% | 19.56% | -137.604
89 | Mohamed Ahmed Mamdouh Mohamed Zakzouk | Landscape | 18187 | 9710 | 2025-01-30 | 48068.78 | NS-01A | Rafik | Maryam Samy | Ulfat | Redsea Marine | 120 | 30% | 1382875.2 | 20% | 43.42% | 572508.936
90 | Mohamed Ahmed Mamdouh Mohamed Zakzouk | Pool | 18188 | 9711 | 2025-01-30 | 51059.4 | NS-01A | Rafik | Maryam Samy | Youssef El sheaty | Redsea Marine | 150 | 30% | 1320584.67 | 20% | 49.14% | 756454.538
91 | Mohamed Hamdy Hassan | Unit Extension | 18214 | 9712 | 2025-01-30 | 82766.25 | Y-183 | Ahmed Sallam | Nader ElGendy | Malak | Maintenance | 120 | 30% | 1073278.51 | 55% | 74.5% | 820568.063
92 | Mohamed Hamdy Hassan | Interiors | 18215 | 9713 | 2025-01-30 | 18597.22 | Y-183 | Ahmed Sallam | Nader ElGendy | Hesham Emshaty | Maintenance | 120 | 30% | 661979.91 | 20% | 30% | 94534.17
93 | Mohamed Hamdy Hassan | Interiors | 18216 | 9714 | 2025-01-30 | 8227.79 | Y-183 | Ahmed Sallam | Nader ElGendy | Menna Middany | Maintenance | 90 | 30% | 253551.15 | 20% | 39.4% | 81146.13
94 | Samah Afifi | Pool | 18179 | 9715 | 2025-01-30 | 28366.8 | CY-292C | Ahmed Essam | Engy Sameh | Mazen Kamal | Redsea golf | 120 | 30% | 381494.93 | 20% | 73.55% | 772434.726
95 |  | Design Fees | 3832 | 9716 | 2025-01-30 | 11400 | Y-118 | #N/A |  | Yehia | Design Fees | 0 | 30% | 0 | 20% | #N/A | #N/A
96 | Ahmed Salama | Interiors | 18220 | 9717 | 2025-01-30 | 1125.6 | GV-02 | Ahmed Essam | Engy Sameh | Farah | Redsea Marine | 30 | 30% | 50107.05 | 20% | 12.45% | -4318.906
97 | Ahmed Mostafa Ahmed Salem | SOG | 18136 | 9718 | 2025-01-30 | 8608.19 | CY-277 | Mostafa | Maryam Samy | Ulfat | Maintenance | 60 | 30% | 364654.24 | 20% | 16.69% | -14482.712
98 | Karim Nour | Interiors | 18200 | 9719 | 2025-01-30 | 14007.25 | FD-225 | Peter | Eng. Peter Philip | Youssef El sheaty | Redsea golf | 60 | 30% | 534033.2 | 20% | 25.02% | 35766.04
99 | Ahmed Mohamed Atris Mohamed Abo Dala | Softscape | 18224 | 9720 | 2025-01-31 | 6065.65 | GV-63 | Rafik | Engy Sameh | Malak | Softscape | 30 | 30% | 233475.36 | 20% | 24.3% | 13268.488
100 | Mohamed Tarek Helmy Hassan Nassar / Mariam Tarek Helmy Hassan Nassar | Shutter | 18197 | 9722 | 2025-01-31 | 10356.42 | ASV-172 | Ahmed Sallam | Haidy Ali | Hesham Emshaty | External | 60 | 30% | 399073.5 | 20% | 24.22% | 22214.068
101 | Kirill Diakovskii | Infrastructure | 18167 | 9723 | 2025-01-31 | 2178 | FD-202 | Mohamed Assal | Maryam Samy | Menna Middany | Redsea golf | 30 | 30% | 83359.5 | 20% | 24.73% | 5239.1
102 | Montaser Salah Mohamed Ali | SOG | 18233 | 9724 | 2025-02-03 | 1496.73 | CY-274 | Mostafa | Maryam Samy | Mazen Kamal | Redsea golf | 30 | 30% | 58768.5 | 20% | 22.78% | 2116.804
103 | Shima Elhusieny | Interiors | 18230 | 9725 | 2025-02-03 | 83267.75 | AH-104 | Omar Nada | Engy Sameh | Yehia | External | 30 | 30% | 3601526.83 | 20% | 14.94% | -214288.022
104 | Hisham Ahmed Mahmoud Oukasha | Softscape | 18227 | 9726 | 2025-02-04 | 1965.17 | AH-8A-0 | Omar Nada | Maryam Samy | Farah | Softscape | 30 | 30% | 75504.19 | 20% | 24.44% | 4436.722
105 | Mohamed Abdelfattah El Metwally Abdelfattah diab | Landscape | 18238 | 9727 | 2025-02-04 | 2506.35 | K2-3T-3 | Ahmed Nasser | Maryam Samy | Ulfat | Redsea golf | 30 | 30% | 76433.28 | 20% | 40.03% | 25522.232
106 | Ahmed Mohamed Mahmoud El Morsy | Landscape | 18203 | 9728 | 2025-02-05 | 6998.62 | AH-47B | Youssef | Maryam Samy | Youssef El sheaty | Redsea golf | 90 | 30% | 222703.95 | 20% | 37.42% | 61992.074
107 | Walid lotfy Ahmed | SOG | 18202 | 9729 | 2025-02-05 | 6624.07 | AH-5B | Omar Nada | Haidy Ali | Malak | Maintenance | 30 | 30% | 293286.83 | 20% | 12.93% | -23827.078
108 | Danishmand Ahmad | Interiors | 18240 | 9730 | 2025-02-05 | 943.74 | Ph4-Villa-3 | Rafik | Eng. Peter Philip | Hesham Emshaty | External | 30 | 30% | 22000.65 | 20% | 54.15% | 16389.638
109 |  | Design Fees | 18234 | 9731 | 2025-02-05 | 14575 | W-58 | #N/A | Eng. Peter Philip | Menna Middany | Redsea golf | 0 | 30% | 0 | 20% | 100% | 592894.68
110 | Mohamed Radwan | SOG | 18211 | 9732 | 2025-02-05 | 1281 | ASV-17A | Ahmed Sallam | Engy Sameh | Mazen Kamal | Redsea golf | 40 | 30% | 60868.5 | 20% | 6.553% | -8758.852
111 | Mohamed Hamdy Hassan | Unit Extension | 18182 | 9733 | 2025-02-05 | 39835.83 | Y-183 | Ahmed Sallam | Nader ElGendy | Yehia | Maintenance | 120 | 30% | 773341.8 | 55% | 61.82% | 138176.4855
112 | Karim ElTorkey | SOG | 18242 | 9734 | 2025-02-09 | 767.81 | K2-4C-0-5 | Ahmed Nasser | Eng. Peter Philip | Farah | Redsea golf | 30 | 30% | 22204.88 | 20% | 43.13% | 9028.768
113 | Hnaa Marwan Mohamed Ahmed El Smak / Marwan Mahmoud Ahmed Mohamed Ibrahim El Smak | Interiors | 18243 | 9735 | 2025-02-09 | 1100.33 | FM18A-0-1 | Peter | Engy Sameh | Ulfat | Redsea Marine | 30 | 30% | 35332.5 | 20% | 36.85% | 9427.692
114 | Wael Mahmoud Lotfy | Interiors | 18249 | 9736 | 2025-02-09 | 1951.95 | AH-96 | Moataz | Eng. Peter Philip | Youssef El sheaty | Redsea golf | 30 | 30% | 76681.5 | 20% | 21.79% | 1754.1
115 | Ayman Gerges | Pool | 18218 | 9737 | 2025-02-09 | 6280.05 | K1-3T-2 | Ahmed Nasser | Haidy Ali | Malak | Redsea golf | 90 | 30% | 241736.25 | 20% | 23.37% | 10616.254
116 | Evelin Adly Said-Saad Sobhy Saad Gawargy | SOG | 18209 | 9738 | 2025-02-10 | 2619.61 | S-80C | Rafik | Haidy Ali | Hesham Emshaty | Redsea golf | 30 | 30% | 93728.62 | 20% | 28.77% | 11535.692
117 | Jylan Khairat | Shutter | 18225 | 9739 | 2025-02-10 | 1269.59 | K2-2C-0-2 | Ahmed Nasser | Haidy Ali | Menna Middany | Redsea golf | 30 | 30% | 49392 | 20% | 22.55% | 1624.192
118 | Andrew Emad | Pool | 18246 | 9740 | 2025-02-10 | 28717.5 | CY-282A | Mostafa | Maryam Samy | Mazen Kamal | External | 80 | 30% | 16680 | 20% | 98.84% | 1137281.048
120 | George-Kerolos Malky Abdel Malak | Design Fees | 18239 | 9742 | 2025-02-10 | 210 | CY-275 | #N/A | Maryam Samy | Yehia | Design Fees | 0 | 30% | 0 | 20% | 100% | 8438.472
121 | Nader Rafaat Wagdi Ragheb | Landscape | 18180 | 9743 | 2025-02-10 | 492.32 | GV-24 | Rafik | Engy Sameh | Farah | Redsea Marine | 30 | 30% | 19792.51 | 20% | 19.96% | -9.518
122 | Youssef Mohamed Ashraf Salah El Din Helmy / Mariam Mohamed Ashraf Salah El Din Helmy | SOG | 18173 | 9744 | 2025-02-10 | 8914.66 | ASV-144B | Ahmed Sallam | Haidy Ali | Ulfat | External | 45 | 30% | 353435.25 | 20% | 21.07% | 4784.318
123 | Sherif Moustafa Youssef Zohny | SOG | 18254 | 9745 | 2025-02-11 | 4110.95 | GV-64 | Rafik | Maryam Samy | Youssef El sheaty | Redsea Marine | 30 | 30% | 155177.09 | 20% | 24.85% | 10014.038
124 | Hany Sayed Madbouly Aly Hassan | Interiors | 18248 | 9746 | 2025-02-11 | 2470.47 | FD1A-1-5 | Engy | Nader ElGendy | Malak | External | 30 | 30% | 89315.1 | 20% | 28.02% | 9956.292
125 | Ahmed Mohamed El Sayed Mohamed Gad | Design Fees | 18244 | 9747 | 2025-02-11 | 228 | ASV-83B | #N/A | Maryam Samy | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
126 | Mohamed Moustafa Mansur EL AHWAL | Pool | 18229 | 9748 | 2025-02-11 | 5542.72 | ASV-117 | Ahmed Sallam | Nader ElGendy | Menna Middany | Redsea golf | 60 | 30% | 213346.88 | 20% | 23.37% | 9377.344
127 | Mohamed Hamdy Hassan | Roof Room | 18156 | 9749 | 2025-02-12 | 76753.95 | Y-183 | Ahmed Sallam | Nader ElGendy | Mazen Kamal | Maintenance | 120 | 30% | 1262245.94 | 60% | 67.26% | 279863.72
128 | Bader Mahmoud Bader Abu Zaid | SOG | 18245 | 9750 | 2025-02-12 | 14983.13 | ASV-111 | Mohamed Assal | Engy Sameh | Yehia | Maintenance | 60 | 30% | 557549.63 | 20% | 25.92% | 44520.482
129 | Karim Nour | Softscape | 18255 | 9751 | 2025-02-12 | 104401.24 | FD-225 | Nesma | Eng. Peter Philip | Farah | Softscape | 45 | 30% | 3808575.74 | 20% | 27.37% | 386600.164
130 | Karim Nour | Landscape | 18256 | 9752 | 2025-02-12 | 203903.61 | FD-225 | Nesma | Eng. Peter Philip | Ulfat | Redsea golf | 90 | 30% | 7848804.6 | 20% | 23.37% | 344694.944
131 | Tarek Hammoud | Landscape | 18183 | 9753 | 2025-02-12 | 19489.93 | K3-2T-4 | Ahmed Nasser | Maryam Samy | Youssef El sheaty | Redsea golf | 60 | 30% | 714259.35 | 20% | 27.04% | 68908.402
132 | Mariam Mohamed Kassem Ahmed El Samny | SOG | 18267 | 9754 | 2025-02-12 | 3518.13 | S78-0-1 | Rafik | Eng. Peter Philip | Malak | Redsea Marine | 30 | 30% | 136134.6 | 20% | 22.96% | 5235.12
133 | Bassem darwish | Roof Room | 18175 | 9755 | 2025-02-12 | 57607.08 | K1-2T-2 | Ahmed Nasser | Eng. Peter Philip | Hesham Emshaty | Redsea golf | 120 | 30% | 978075 | 60% | 66.2% | 179343.408
134 | Loanns Gregory Gregoriou | Softscape | 18232 | 9756 | 2025-02-14 | 6742.86 | ASV-176B | Ahmed Sallam | Nader ElGendy | Menna Middany | Softscape | 60 | 30% | 156271.49 | 20% | 53.86% | 114678.198
135 |  | Design Fees | 18199 | 9757 | 2025-02-15 | 228 | Y-125 | #N/A | Maryam Samy | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
136 | Ashraf Adel Fouad Ramzy | Landscape | 18276 | 9758 | 2025-02-15 | 408.19 | CY-211A | Mostafa | Nader ElGendy | Yehia | Maintenance | 30 | 30% | 12940.42 | 20% | 36.89% | 3461.964
137 | Hesham Elbeltagy | SOG | 18281 | 9759 | 2025-02-16 | 1701.37 | K1-1C-0-2 | Ahmed Nasser | Engy Sameh | Farah | Redsea golf | 60 | 30% | 47103 | 20% | 44.88% | 21263.488
138 | Mammdouh Ismail-Maram Mostafa Hamed | SOG | 18278 | 9760 | 2025-02-17 | 1791.62 | K1-5C-0-6 | Ahmed Nasser | Maryam Samy | Ulfat | Redsea golf | 30 | 30% | 62270.25 | 20% | 30.8% | 9722.774
139 | Hans Honore Charles & Joachim Boudewijn Wilfried | Interiors | 18277 | 9761 | 2025-02-17 | 190.52 | Ph4-Villa-4B | Rafik | Nader ElGendy | Youssef El sheaty | Redsea golf | 30 | 30% | 2520 | 20% | 73.67% | 5135.704
140 | Micheal Mourad Mounir Nassif / Madonna Mourad Mounir Nassif | Shutter | 18274 | 9762 | 2025-02-17 | 2192.24 | K2-1C-1-7 | Ahmed Nasser | Engy Sameh | Malak | External | 30 | 30% | 81774 | 20% | 25.74% | 6317.216
141 | hassan tamraz | Interiors | 18257 | 9763 | 2025-02-18 | 36362.63 | JE-20 | Mostafa | Eng. Peter Philip | Hesham Emshaty | External | 40 | 30% | 1552172.05 | 20% | 15.02% | -91005.218
143 | Hatem Ahmed Ehsan Kotby / Sally Nabile Mohamed Shehata | Heater | 18282 | 9765 | 2025-02-18 | 15605.72 | GV-65B | Rafik | Maryam Samy | Menna Middany | External | 30 | 30% | 509580 | 20% | 34.99% | 117507.768
144 | Wael Mahmoud Lotfy | Design Fees | 18287 | 9766 | 2025-02-18 | 2394 | AH-96 | #N/A | Eng. Peter Philip | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 96198.584
145 | Khaled SOLIMAN | Shutter | 18288 | 9767 | 2025-02-19 | 8111.96 | AH-4 | Omar Nada | Engy Sameh | Yehia | External | 30 | 30% | 322318.5 | 20% | 20.89% | 3646.012
146 | Ahmed Hamdy Abou Hashima | Interiors | 18261 | 9768 | 2025-02-19 | 20452.37 | Ph3-Villa-21 | Mohamed Assal | Engy Sameh | Farah | External | 70 | 30% | 0 | 20% | 100% | 821841.672
147 | Ahmed Hamdy Abou Hashima | Landscape | 18273 | 9769 | 2025-02-19 | 3234.53 | Ph3-Villa-21 | Mohamed Assal | Engy Sameh | Ulfat | Redsea golf | 60 | 30% | 130000.5 | 20% | 19.98% | -26.732
148 | Ahmed Hamdy Abou Hashima | Landscape | 18263 | 9770 | 2025-02-19 | 8715.32 | Ph3-Villa-21 | Mohamed Assal | Engy Sameh | Youssef El sheaty | External | 70 | 30% | 0 | 20% | 100% | 350209.448
150 | Wassim Alme | Roof Room | 18128 | 9772 | 2025-02-19 | 105793.33 | CY-292A | Ahmed Essam | Haidy Ali | Malak | Redsea golf | 120 | 30% | 1433538.75 | 60% | 73.02% | 692018.518
151 | Sherif Abdalla | Outdoor Room | 18289 | 9773 | 2025-02-19 | 61754.08 | AH-93 | Engy | Maryam Samy | Hesham Emshaty | Redsea golf | 120 | 30% | 857496.15 | 40% | 72.36% | 1003611.258
152 | Wael Mohamed Mohamed Sayed Khalil | Outdoor Room | 18290 | 9774 | 2025-02-20 | 112875 | Y-74 | Nesma | Eng. Peter Philip | Menna Middany | External | 120 | 30% | 1486474.59 | 40% | 73.78% | 1915284.438
156 | Manal Yousef Mahmoud -Sherif Mansour | Design Fees | 18305 | 9778 | 2025-02-20 | 228 | K2-5T-6 | #N/A | Eng. Peter Philip | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
158 |  | Design Fees | 18307 | 9780 | 2025-02-20 | 3306 | AH-68 | #N/A | Eng. Peter Philip | Yehia | Design Fees | 0 | 30% | 0 | 20% | 100% | 132845.656
159 | Tarek Riad | SOG | 18304 | 9781 | 2025-02-20 | 651 | ASV-183 | Ahmed Sallam | Engy Sameh | Farah | External | 30 | 30% | 0 | 20% | 100% | 26159.264
160 | Abanoub Eid Youseef Ghatas | SOG | 18311 | 9782 | 2025-02-20 | 594.56 | K2-2C-0-4 | Ahmed Nasser | Engy Sameh | Ulfat | Redsea golf | 30 | 30% | 18942 | 20% | 36.57% | 4949.32
161 | Hnaa Marwan Mohamed Ahmed El Smak / Marwan Mahmoud Ahmed Mohamed Ibrahim El Smak | Pool | 18300 | 9783 | 2025-02-20 | 494.81 | FM18A-0-1 | Peter | Engy Sameh | Youssef El sheaty | Redsea Marine | 30 | 30% | 18742.5 | 20% | 24.59% | 1140.548
162 | Hnaa Marwan Mohamed Ahmed El Smak / Marwan Mahmoud Ahmed Mohamed Ibrahim El Smak | Interiors | 18299 | 9784 | 2025-02-20 | 8638.35 | FM18A-0-1 | Peter | Engy Sameh | Malak | External | 60 | 30% | 353197.14 | 20% | 18.6% | -6080.596
163 | Barbara Abdo Spiro Nagiub | Landscape | 18301 | 9785 | 2025-02-21 | 1829.46 | FM15B-0-1 | Peter | Haidy Ali | Hesham Emshaty | Redsea Marine | 30 | 30% | 57750 | 20% | 37.15% | 15763.56
164 | Soraya El Sayed Farouk Abdallah abouhussein | Design Fees | 18201 | 9786 | 2025-02-22 | 210 | GV-65C | #N/A | Maryam Samy | Menna Middany | Design Fees | 0 | 30% | 0 | 20% | 100% | 8438.472
165 |  | Design Fees | 18306 | 9787 | 2025-02-22 | 228 | Ph2-Villa-24 | #N/A | Engy Sameh | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
166 | Soraya El Sayed Farouk Abdallah abouhussein | SOG | 18298 | 9788 | 2025-02-23 | 3154.94 | GV-65C | Rafik | Maryam Samy | Yehia | Redsea Marine | 30 | 30% | 123511.5 | 20% | 22.06% | 3264.084
167 | George Sedky Samuel Henein | Shutter | 18312 | 9789 | 2025-02-23 | 1996.12 | K3-1C-1-6 | Ahmed Nasser | Engy Sameh | Farah | External | 30 | 30% | 74119.5 | 20% | 26.08% | 6090.988
168 | Ahmed Magdy Ahmed Mohamed Awadallah / Sionara Taher Ezzat El Asmar | Landscape | 18319 | 9790 | 2025-02-23 | 779.1 | CY-284 | Mostafa | Maryam Samy | Ulfat | Redsea golf | 30 | 30% | 27415.5 | 20% | 29.94% | 3891.228
169 | Kirill Diakovskii | SOG | 18310 | 9791 | 2025-02-23 | 17448.09 | ASV-164 | Nesma | Haidy Ali | Youssef El sheaty | Maintenance | 60 | 30% | 717789.41 | 20% | 18.1% | -16669.322
170 | Hossam Allam | SOG | 18275 | 9792 | 2025-02-24 | 17176.85 | AH-98 | Youssef |  | Malak | Redsea golf | 40 | 30% | 585863.25 | 20% | 32.1% | 104357.55
171 | Amr Yehia | Interiors | 18309 | 9793 | 2025-02-24 | 1696.87 | FM3B-1-1 | Peter | Nader ElGendy | Hesham Emshaty | Redsea Marine | 30 | 30% | 68985 | 20% | 19.06% | -799.336
172 | Mustafa Ali Abul-Nasr | Landscape | 18334 | 9794 | 2025-02-25 | 397.22 | GV-46A | Rafik | Haidy Ali | Menna Middany | Redsea Marine | 30 | 30% | 15337.47 | 20% | 23.13% | 624.098
173 | ihab roushdy | SOG | 18328 | 9795 | 2025-02-25 | 8006.87 | AH-40B | Engy | Nader ElGendy | Mazen Kamal | Redsea golf | 30 | 30% | 351587.25 | 20% | 12.58% | -29845.594
174 | Salwa Ahmed El Awady | Landscape | 18329 | 9796 | 2025-02-25 | 14894.25 | CY-201 | Mostafa | Haidy Ali | Yehia | Redsea golf | 60 | 30% | 565494.3 | 20% | 24.41% | 33004.324
175 | peter Salah | Interiors | 18331 | 9797 | 2025-02-25 | 982.05 | K1-4T-5 | Ahmed Nasser | Maryam Samy | Farah | Redsea golf | 30 | 30% | 29799 | 20% | 39.59% | 9662.912
176 | Mariam Mikhail | Design Fees | 18340 | 9798 | 2025-02-25 | 228 | S64-0-1 | #N/A | Engy Sameh | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
177 | Venes Farouk | Landscape | 18206 | 9799 | 2025-02-26 | 672 | GV-31 | Rafik | Haidy Ali | Youssef El sheaty | Redsea Marine | 30 | 30% | 23887.5 | 20% | 29.23% | 3115.612
179 | Alyia Salah ElDin | Unit Extension | 18292 | 9801 | 2025-02-26 | 79931.46 | W-88 | Mostafa | Nader ElGendy | Malak | Profit | 120 | 30% | 0 | 55% | 100% | 1806694.785
181 | Amani Osama Kamel Hassan / Ahmed Hassan Hosny Ahmed El Shafei | SOG | 18341 | 9803 | 2025-02-26 | 6414.02 | CY-272A | Mostafa | Engy Sameh | Hesham Emshaty | Redsea golf | 40 | 30% | 193307.1 | 20% | 40% | 64428.748
182 | Ahmed Natout | Design Fees | 18342 | 9804 | 2025-02-26 | 199.5 | ASV-124 | #N/A | Engy Sameh | Menna Middany | Design Fees | 0 | 30% | 0 | 20% | 100% | 8016.552
183 | Hazem Hassan Saad Mahmoud Saad | Interiors | 18347 | 9805 | 2025-02-26 | 6117.72 | Ph4-Villa-40 | Rafik | Engy Sameh | Mazen Kamal | External | 30 | 30% | 220395 | 20% | 28.28% | 25434.568
184 | Inji Al Sayed Refaat | SOG | 18176 | 9806 | 2025-02-26 | 390.6 | CY-130D | Mostafa | Nader ElGendy | Yehia | Redsea golf | 35 | 30% | 12629.93 | 20% | 35.63% | 3065.63
185 |  | Design Fees | 18350 | 9807 | 2025-02-26 | 228 | AH-14A | #N/A | Maryam Samy | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
186 |  | Design Fees | 18111 | 9808 | 2025-02-26 | 57000 | Y-127 | #N/A | Maryam Samy | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 45600
187 | Atito Ahmed Abu Eraki | SOG | 18291 | 9809 | 2025-02-26 | 6818.53 | ASV-92 | Nesma | Maryam Samy | Youssef El sheaty | Maintenance | 45 | 30% | 258199.39 | 20% | 24.61% | 15790.962
188 | Karim Mohamed Alaa El Din | Softscape | 18284 | 9810 | 2025-02-26 | 8241.62 | ASV-166 | Ahmed Sallam | Haidy Ali | Malak | Softscape | 30 | 30% | 313965.77 | 20% | 24.16% | 17208.894
189 | Sherif Abdel Moneim Awad Ali | Roof Room | 18332 | 9811 | 2025-02-26 | 98915.78 | FD-212 | Youssef | Haidy Ali | Hesham Emshaty | Maintenance | 120 | 30% | 66060.46 | 60% | 98.67% | 1921315.824
190 | The Egyptian International Tourism (Ashraf Labib) | Pool | 18127 | 9812 | 2025-02-27 | 36068.69 | y-155 | Nesma | Eng. Peter Philip | Menna Middany | Redsea golf | 60 | 30% | 1048706.4 | 20% | 42.11% | 400648.984
191 | Fouad John Tawfik Fouad Matouk | Interiors | 18018 | 9813 | 2025-02-27 | 1344966.86 | ASV-115 | Peter | Haidy Ali | Mazen Kamal | Redsea golf | 90 | 30% | 1061161.5 | 20% | 21.1% | 14811.988
193 | Amr Ibrahim Elsayed Morsi | Landscape | 18030 | 9815 | 2025-02-27 | 579392.35 | CY-30 | Rafik | Hanine Fakher | Yehia | Profit | 40 | 30% | 0 | 20% | 100% | 463513.88
194 | ibrahim mohsen | Pool | 18323 | 9816 | 2025-02-27 | 8530.74 | GE-34 | Rafik | Haidy Ali | Farah | Redsea golf | 60 | 30% | 224240.1 | 20% | 47.67% | 118552.332
195 | Ahmed Mohamed Saad -Marim Ryad Saad | SOG | 18295 | 9817 | 2025-02-27 | 1481.81 | AH-31A | Omar Nada | Haidy Ali | Ulfat | Redsea golf | 30 | 30% | 49822.5 | 20% | 33.06% | 9721.364
196 |  | Design Fees | 18149 | 9818 | 2025-02-27 | 11400 | FD-209 | #N/A | Maryam Samy | Youssef El sheaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 9120
197 | Mariam Mikhail | SOG | 18356 | 9819 | 2025-02-27 | 2033.01 | S64-0-1 | Rafik | Engy Sameh | Malak | Redsea Marine | 30 | 30% | 65555.7 | 20% | 35.8% | 16137.148
198 | Nabil Tarek Mahmoud Ali El Deeb | Softscape | 18357 | 9820 | 2025-02-27 | 699.56 | K3-3C-0-2 | Ahmed Nasser | Engy Sameh | Hesham Emshaty | Softscape | 30 | 30% | 28080.14 | 20% | 20.09% | 30.42
199 | Nabil Tarek Mahmoud Ali El Deeb | SOG | 18358 | 9821 | 2025-02-27 | 631.31 | K3-3C-0-2 | Ahmed Nasser | Engy Sameh | Menna Middany | Redsea golf | 40 | 30% | 80671.5 | 20% | -154.4% | -55303.444
200 | Salma Mouslim Mohamed Mouslim / Yassmin Mouslim Mohamed Mouslim | SOG | 18361 | 9822 | 2025-02-27 | 6079.5 | AH-19A | Omar Nada | Maryam Samy | Mazen Kamal | Redsea golf | 30 | 30% | 187708.5 | 20% | 38.53% | 56585.268
201 | Chirstiana Salentin-Peev | Shutter | 18250 | 9823 | 2025-02-27 | 2475.63 | K4-2C-2-10 | Ahmed Nasser | Engy Sameh | Yehia | External | 30 | 30% | 93644.25 | 20% | 24.69% | 5834.486
202 | Hany Shawky | SOG | 18349 | 9824 | 2025-02-27 | 6443.72 | CY-232D | Engy | Maryam Samy | Farah | Redsea golf | 40 | 30% | 203096.25 | 20% | 37.25% | 55833.038
203 |  | Design Fees | 18362 | 9825 | 2025-02-27 | 228 | CY-258 | #N/A | Engy Sameh | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
206 | Henein Antoun Baracat | Interiors | 18184 | 9828 | 2025-02-27 | 475.9 | W-11A | Ahmed Hashad | Maryam Samy | Youssef El sheaty | Redsea golf | 30 | 30% | 19300.05 | 20% | 20.25% | 59.942
207 | Samia Rashed Iskander | Outdoor Room | 18335 | 9829 | 2025-02-27 | 42875 | K1-3T-4 | Ahmed Nasser | Maryam Samy | Malak | Redsea golf | 120 | 30% | 730170 | 40% | 66.09% | 561971.028
211 | Shahinaz Salama Gouda Mohamed El Shaer | Design Fees | 18338 | 9833 | 2025-02-28 | 228 | CY-289A | #N/A | Engy Sameh | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 9161.768
212 | Lamia Rabie | Pool | 18360 | 9834 | 2025-02-28 | 21853.65 | GV-65A | Rafik | Nader ElGendy | Menna Middany | Redsea Marine | 120 | 30% | 576393.25 | 20% | 47.49% | 301756.342
213 | Shahinaz Salama Gouda Mohamed El Shaer | SOG | 18354 | 9835 | 2025-02-28 | 1472.63 | CY-289A | Mostafa | Engy Sameh | Mazen Kamal | Redsea golf | 40 | 30% | 54463.5 | 20% | 26.37% | 4711.484
214 | Hala Helmy El Saeed Younes | Landscape | 18375 | 9837 | 2025-03-03 | 1520.91 | ASV-120 | Peter | Maryam Samy | Yehia | Redsea golf | 30 | 30% | 43575 | 20% | 43.46% | 18076
215 |  | Design Fees | 18368 | 9838 | 2025-03-03 | 228 | T1-12D | #N/A | Maryam Samy | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 9242.12
216 | Youmna Khalil | Landscape | 18369 | 9839 | 2025-03-03 | 9962.02 | S-16D | Rafik | Maryam Samy | Ulfat | Redsea golf | 70 | 30% | 312068.48 | 20% | 38.18% | 91747.976
217 | Ayman Ismail | Landscape | 18372 | 9840 | 2025-03-03 | 4377.57 | ASV-194B | Ahmed Sallam | Maryam Samy | Youssef El sheaty | External | 30 | 30% | 80419.5 | 20% | 63.74% | 97027.924
218 | Duncan Keith Howard | Interiors | 18385 | 9841 | 2025-03-04 | 279.67 | CY-8 | Rafik | Engy Sameh | Malak | Redsea golf | 30 | 30% | 11371.5 | 20% | 19.75% | -34.908
221 | Kirill Diakovskii | Interiors | 18390 | 9844 | 2025-03-06 | 6143.76 | FD-202 | Mohamed Assal | Maryam Samy | Hesham Emshaty | External | 60 | 30% | 241500 | 20% | 22.42% | 7541
222 | Karim Mohamed Affify El Said | Landscape | 18389 | 9845 | 2025-03-06 | 634.41 | Hill-Villa-113 | Peter | Hanine Fakher | Menna Middany | Maintenance | 30 | 30% | 21407.38 | 20% | 33.4% | 4308.812
224 | Aliaa Omar | Interiors | 18198 | 9847 | 2025-03-09 | 4811.1 | ASV-186 | Moataz | Eng. Peter Philip | Mazen Kamal | Profit | 70 | 30% | 0 | 20% | 100% | 195020.824
225 | Tarek El Gindy | Outdoor Room | 18236 | 9848 | 2025-03-09 | 112000 | W-24 | Peter | Nader ElGendy | Yehia | Maintenance | 90 | 30% | 2008333.75 | 40% | 64.61% | 1396656.65
226 | Dina Kamel | Design Fees | 18407 | 9849 | 2025-03-09 | 165.3 | K2-3T-4 | #N/A | Maryam Samy | Farah | Design Fees | 0 | 30% | 0 | 20% | 100% | 6700.536
227 | hussein badawy | Landscape | 18394 | 9850 | 2025-03-09 | 14021.02 | GV-67 | Ahmed Essam | Maryam Samy | Ulfat | Redsea Marine | 60 | 30% | 525948.15 | 20% | 25.97% | 42402.306
228 | Ahmed Mohamed Atris Mohamed Abo Dala | Shutter | 18402 | 9851 | 2025-03-09 | 521.03 | GV-63 | Rafik | Engy Sameh | Youssef El sheaty | External | 30 | 30% | 21000 | 20% | 20.46% | 120.264
230 | Kirollos Samir Teriak Eid | SOG | 18293 | 9854 | 2025-03-09 | 9603.5 | ASV-174A | Ahmed Sallam | Haidy Ali | Malak | External | 60 | 30% | 366891 | 20% | 24.6% | 22392.632
231 |  | Design Fees | 18386 | 9855 | 2025-03-10 | 3306 | AH-90 | #N/A | Engy Sameh | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 134010.696
232 | Geraldine Dawood Soleiman Gerges Boktor | SOG | 17862 | 9856 | 2025-03-10 | 422985.94 | S-37 | Rafik | Maryam Samy | Menna Middany | Profit | 30 | 30% | 0 | 20% | 100% | 338388.752
234 |  | Design Fees | 18383 | 9858 | 2025-03-10 | 228 | S-48 | #N/A | Engy Sameh | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 9242.12
237 | Ahmed Mohamed El Sayed Mohamed Gad | SOG | 18396 | 9861 | 2025-03-11 | 2225.41 | ASV-83B | Ahmed Sallam | Maryam Samy | Yehia | Redsea golf | 30 | 30% | 78676.5 | 20% | 30.23% | 11531.828
240 | Nayer Alaoui Gamil Fouad | Heater | 18223 | 9864 | 2025-03-11 | 1260.02 | FM5A-1-1 | Peter | Nader ElGendy | Farah | Profit | 30 | 30% | 0 | 20% | 100% | 51075.664
241 | Sherif Sawalhy | SOG | 18405 | 9865 | 2025-03-11 | 10154.34 | GV-27 | Rafik | Haidy Ali | Ulfat | Redsea Marine | 30 | 30% | 342730.5 | 20% | 33.39% | 68881.764
242 |  | Design Fees | 18404 | 9866 | 2025-03-11 | 228 | GV-66C | #N/A | Maryam Samy | Youssef El sheaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 9242.12
243 |  | Design Fees | 18377 | 9867 | 2025-03-11 | 228 | CY-225 | #N/A | Maryam Samy | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 9242.12
244 | George-Kerolos Malky Abdel Malak | SOG | 18419 | 9868 | 2025-03-12 | 6174.86 | CY-275 | Engy | Maryam Samy | Hesham Emshaty | Redsea golf | 60 | 30% | 219520.88 | 20% | 29.84% | 30780.776
245 | Emad Fawzy Tawadros Salib | SOG | 18422 | 9869 | 2025-03-12 | 10503.39 | GV-71B | Rafik | Engy Sameh | Menna Middany | Redsea Marine | 70 | 30% | 305991 | 20% | 42.5% | 119770.216
246 | Amr barhoma | Design Fees | 18384 | 9870 | 2025-03-12 | 2394 | CY-231A | #N/A | Eng. Peter Philip | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 97042.224
247 | Amr barhoma | Shutter | 18414 | 9871 | 2025-03-12 | 3752.49 | CY-231A | Engy | Eng. Peter Philip | Yehia | External | 30 | 30% | 145551 | 20% | 23.45% | 6558.432
248 | Kirill Diakovskii | Interiors | 18425 | 9872 | 2025-03-12 | 1072.4 | FD-202 | Mohamed Assal | Maryam Samy | Farah | Redsea golf | 30 | 30% | 12987.45 | 20% | 76.02% | 30337.51
249 |  | Design Fees | 18415 | 9873 | 2025-03-12 | 912 | Ph4-Villa-32B | #N/A | Engy Sameh | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 36968.464
250 | Fouad John Tawfik Fouad Matouk | Interiors | 18395 | 9874 | 2025-03-13 | 396.36 | ASV-115 | Peter | Haidy Ali | Youssef El sheaty | Redsea golf | 80 | 30% | 16117.5 | 20% | 19.75% | -50.812
251 |  | Design Fees | 18348 | 9875 | 2025-03-13 | 228 | AH-16B-0 | #N/A | Engy Sameh | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 9242.12
252 |  | Design Fees | 18330 | 9876 | 2025-03-13 | 855 | Ph5-Villa-6 | #N/A | Maryam Samy | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 34657.936
254 | Mina Samir Drias Habashi | Shutter | 18221 | 9878 | 2025-03-14 | 2353.37 | S64-0-3 | Rafik | Hanine Fakher | Menna Middany | External | 30 | 30% | 80199 | 20% | 32.74% | 15196.264
255 | Fouad John Tawfik Fouad Matouk | Landscape | 18428 | 9879 | 2025-03-14 | 1642.99 | ASV-115 | Peter | Haidy Ali | Mazen Kamal | Redsea golf | 45 | 30% | 63341.25 | 20% | 23.66% | 3035.55
257 | Duncan Keith Howard | Interiors | 18434 | 9881 | 2025-03-14 | 1079.85 | CY-8 | Rafik | Engy Sameh | Yehia | Redsea golf | 40 | 30% | 44231.25 | 20% | 18.89% | -605.306
258 | Karim Nour | Interiors | 18398 | 9882 | 2025-03-14 | 3267.36 | FD-225 | Nesma | Eng. Peter Philip | Farah | Redsea golf | 30 | 30% | 115703.32 | 20% | 30.11% | 16741.08
259 |  | Design Fees | 18427 | 9883 | 2025-03-14 | 228 | K1-2T-4 | #N/A | Maryam Samy | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 9211.2
261 | Ahmed Natout | Heater | 18424 | 9885 | 2025-03-15 | 2899.13 | ASV-124 | Moataz | Engy Sameh | Youssef El sheaty | Redsea golf | 40 | 30% | 99041.25 | 20% | 32.52% | 18375.606
262 |  | Design Fees | 18345 | 9886 | 2025-03-16 | 627 | Hill-Villa-48B | #N/A | Eng. Peter Philip | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 25440
264 | tatiana emilova | Shutter | 18430 | 9888 | 2025-03-16 | 4549.03 | AH-99 | Engy | Engy Sameh | Hesham Emshaty | External | 30 | 30% | 177586.5 | 20% | 22.95% | 6811.164
265 | Bassem darwish | Landscape | 18432 | 9889 | 2025-03-16 | 17539.27 | K1-2T-2 | Ahmed Nasser | Eng. Peter Philip | Menna Middany | Redsea golf | 90 | 30% | 657752.55 | 20% | 25.92% | 52600.514
266 |  | Design Fees | 18439 | 9890 | 2025-03-16 | 2171.7 | 3410 | #N/A | Nader ElGendy | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 88031.16
267 |  | Design Fees | 18420 | 9891 | 2025-03-17 | 228 | CY-268 | #N/A | Maryam Samy | Yehia | Design Fees | 0 | 30% | 0 | 20% | 100% | 9242.12
268 | Khalil Nogim | Interiors | 18442 | 9892 | 2025-03-17 | 38505.87 | Ph2-Villa-4 | Rafik | Engy Sameh | Farah | Maintenance | 90 | 30% | 1465496.42 | 20% | 24.89% | 95362.124
269 |  | Design Fees | 18426 | 9893 | 2025-03-17 | 513 | AH-21 | #N/A | Nader ElGendy | Ulfat | Design Fees | 0 | 30% | 0 | 20% | 100% | 20794.76
271 |  | Pool | 18406 | 9895 | 2025-03-17 | 30836.4 | Ph4-65A | Rafik | Eng. Peter Philip | Youssef El sheaty | Redsea golf | 120 | 30% | 1222308.15 | 20% | 21.77% | 27663.826
272 |  | Design Fees | 18445 | 9896 | 2025-03-18 | 228 | ASV-185B | #N/A | Nader ElGendy | Malak | Design Fees | 0 | 30% | 0 | 20% | 100% | 9234.168
273 | peter Salah | Design Fees | 18451 | 9897 | 2025-03-18 | 157.32 | K1-4T-5 | #N/A | Maryam Samy | Hesham Emshaty | Design Fees | 0 | 30% | 0 | 20% | 100% | 6371.576
275 | hussein badawy | Interiors | 18437 | 9899 | 2025-03-18 | 101306.46 | GV-67 | Rafik | Maryam Samy | Menna Middany | External | 60 | 30% | 4357082.05 | 20% | 15.05% | -254097.482
277 | Denis Louis Pierrer Liquiere | Design Fees | 18457 | 9901 | 2025-03-18 | 214.32 | Ph2-Villa-19 | #N/A | Maryam Samy | Mazen Kamal | Design Fees | 0 | 30% | 0 | 20% | 100% | 8680.112
280 | IBRAHIM FAHMY | Design Fees | 18441 | 9904 | 2025-03-19 | 3306 | NB-008 | #N/A | Nader ElGendy | Yehia | Design Fees | 0 | 30% | 167369.23 | 20% | 0% | -33473.846
281 | hassan tamraz | Landscape | 18461 | 9905 | 2025-03-20 | 21117.48 | JE-20 | Mostafa | Eng. Peter Philip | Farah | Redsea golf | 70 | 30% | 769970.25 | 20% | 27.98% | 85302.894
282 | ismail tamraz | Landscape | 18462 | 9906 | 2025-03-20 | 22491.6 | JE-21 | Mostafa | Eng. Peter Philip | Ulfat | Redsea golf | 70 | 30% | 818952.75 | 20% | 28.08% | 91973.242
283 |  | Shutter | 18429 | 9907 | 2025-03-20 | 5700.64 | CY-258 | Mostafa | Engy Sameh | Youssef El sheaty | External | 40 | 30% | 218468.25 | 20% | 24.3% | 12411.774
284 |  | Shutter | 18343 | 9908 | 2025-03-22 | 1094.88 | WS-D/3-2-5 | Engy | Nader ElGendy | Malak | External | 30 | 30% | 42000 | 20% | 24.29% | 2381.616
285 |  | Landscape | 18467 | 9909 | 2025-03-22 | 19662.93 | JE-22 | Mostafa | Eng. Peter Philip | Hesham Emshaty | Redsea golf | 70 | 30% | 734790 | 20% | 26.19% | 61572.824
288 |  | Design Fees | 18465 | 9912 | 2025-03-23 | 798 | K3-5C-0-4 | #N/A | Engy Sameh | Menna Middany | Design Fees | 0 | 30% | 0 | 20% | 100% | 32319.576
290 | Manal Yousef Mahmoud -Sherif Mansour | SOG | 18474 | 9914 | 2025-03-23 | 4062.62 | K2-5T-6 | Ahmed Nasser | Eng. Peter Philip | Mazen Kamal | Redsea golf | 30 | 30% | 120937.56 | 20% | 41.2% | 43601.472
297 |  | Design Fees | 18483 | 9921 | 2025-03-24 | 988.05 | ASV-42A | #N/A | Maryam Samy | Yehia | Design Fees | 0 | 30% | 0 | 20% | 100% | 40016.736
300 | Malak Sherif Doss | SOG | 18142 | 9924 | 2025-03-24 | 917.24 | CY-96 | Mostafa | Engy Sameh | Farah | Redsea golf | 30 | 30% | 28812 | 20% | 38.01% | 8368.872